## Technology
Technology
S.No | Particular | Qty(Nos) | Cost(Rs/Unit)
| Mobile App Development (Including GPS Tracking) | 1 | ₹500,000
| Content Management System (CMS) | 1 | ₹350,000
| Integration with Wearables (Photo/Video Capture) | 1 | ₹300,000
| Website Customization | 1 | ₹300,000
| Community Interaction Platform | 1 | ₹250,000
| Security and SSL Setup | 1 | ₹200,000
| App Design and User Interface (UI) | 1 | ₹200,000
| Emergency Contacting and Alerts System | 1 | ₹200,000
| Content Creation and Management | 1 | ₹150,000
| Servers | 1 | ₹150,000
| Fake Call and Anonymous Incident Reporting | 1 | ₹150,000
| Testing and Debugging | 1 | ₹100,000
| Place Rating System | 1 | ₹100,000
| SEO Package | 1 | ₹100,000
| Domain Name and Hosting (Per Year) | - | ₹100,000
| Email Hosting (Per Year) | - | ₹50,000
| Cloud Services (Per Year) | - | ₹50,000

## Project Cost
Project Cost
Category | Particular | Qty(nos) | Cost(Rs/Unit) | Total cost(Rs)
Infrastrucuture & Setup | Rented office | 1 | 206000 | 206000
| Furniture (tables with desks, chairs,fan. water dispenser | 1 | 1,50,000 | 150000
| Electricity bills | 1 | 1,39,737.6 | 139737.6
| Installation | 5 | 800 | 20000
| Miscellaneous |  | 30000 | 30000
| Total cost |  |  | 545737.6
Infrastructure & Services | Backend Development for mobile app | 1 | ₹500,000 | 500000
| Content Management System (CMS) | 1 | ₹350,000 | 350000
| Integration with Wearables (Photo/Video Capture) | 1 | ₹300,000 | 300000
| Website Customization | 1 | ₹300,000 | 300000
| Community Interaction Platform | 1 | ₹250,000 | 250000
| Security and SSL Setup | 1 | ₹200,000 | 200000
| App Design and User Interface (UI) | 1 | ₹200,000 | 200000
| Emergency Contacting and Alerts System | 1 | ₹200,000 | 200000
| Content Creation and Management | 1 | ₹150,000 | 150000
| Servers | 1 | ₹150,000 | 150000
| Fake Call and Anonymous Incident Reporting | 1 | ₹150,000 | 150000
| Testing and Debugging | 1 | ₹100,000 | 100000
| Place Rating System | 1 | ₹100,000 | 100000
| SEO Package | 1 | ₹100,000 | 100000
| Domain Name and Hosting (Per Year) | - | ₹100,000 | 100000
| Email Hosting (Per Year) | - | ₹50,000 | 50000
| Cloud Services (Per Year) | - | ₹50,000 | 50000
| Total cost |  |  | 3250000
Application & website related | Domain & Hosting costs |  | 6435 | 6435
| For maintenance | 1 | 35750 | 35750
| Profile management cost |  | 100000 | 100000
| GPS integration |  | 20600 | 20600
| Updates |  | 35750 | 35750
| SEO Package |  | 12155 | 12155
| Email Hosting per year |  | 7150 | 7150
| Cloud storage |  | 21450 | 21450
| Data privacy |  | 50050 | 50050
| Data anlytics tools |  | 28600 | 28600
| User experience testing |  | 100000 | 100000
417940
Marketing & Promotion | 7 |  | 500000 | 500000
| Collaborations and partnerships with NGOs |  | 300000 | 300000
| Content creation for Ads |  | 400000 | 400000
| Ads Platform fees |  | 1,50,000 | 150000
| PPC(Pay Per Click) |  | 20000 | 20000
| Total cost |  |  | 1370000
Logistics Expenses | Food & Travel |  | 1,20,000 | 120000
| Accommodations |  | 75000 | 75000
| Miscellaneous |  | 50000 | 50000
| Total cost |  |  | 245000
Salaries | Web Developers | 2 | 14,00,000 | 1400000
| UI/UX Designer | 1 | 6,00,000 | 600000
| Marketing Specialist | 1 | 6,00,000 | 600000
| Customer Support/Community Manager | 1 | 4,00,000 | 400000
| Finance/Administrative Officer | 1 | 4,00,000 | 500000
| Product Manager | 1 | 5,00,000 | 500000
| Data analyst | 1 | 6,00,000 | 600000
| Cybersecurity specialist | 2 | 1000000 | 2000000
| Legal and compliance expert | 1 | 500000 | 500000
| Total cost |  |  | 7100000
Depreciation & Maintainence | Depreciation & Maintainance |  | 389000 | 389000
| Total cost |  |  | 389000
| Net total cost |  |  | 13317677.6

## Means of Finance
Means of Finance
Sr No | Particulars | Details
1 | Scheme Name | Digital India mission
2 | Total Project Cost | 12667728
3 | Term Loan Amount @ 35% | 4433704.66
| Scheme amount@20% | 2533545.52
| Angel Investors(% equity)@ 15% | 1900159.14
| Subsidy amount@30% | 3800318.28
| Interest Rate | 13.5%
| Loan Tenure (Years) | 6
| Monthly EMI Payable | 90889
| Annual Amount Repaid (₹) | 1099666

## Profitability Analysis
Profitability Analysis
Category | Particular | Year-1 | Year-2 | Year-3 | Year-4 | Year-5
Fixed costs | Rented Office | 206000 | 206000 | 206000 | 206000 | 206000
| Furniture (Tables, Desks, Chairs, Fan, Water Dispenser) | 150000 | 150000 | 150000 | 150000 | 150000
| Electricity Bills | 139737.6 | 139737.6 | 139737.6 | 139737.6 | 139737.6
| Installation | 20000 | 20000 | 20000 | 20000 | 20000
| Miscellaneous | 30000 | 30000 | 30000 | 30000 | 30000
| Domain Name and Hosting (Per Year) | 100000 | 100000 | 100000 | 100000 | 100000
| Email Hosting (Per Year) | 50000 | 50000 | 50000 | 50000 | 50000
| Cloud Services (Per Year) | 50000 | 50000 | 50000 | 50000 | 50000
| Total Fixed Cost | 545737.6 | 545737.6 | 545737.6 | 545737.6 | 545737.6
Operational cost | Office and Utilities
| Rented Office | 206000 | 216300 | 227115 | 238471 | 250394
| Electricity Bills | 139737.6 | 146724.48 | 154058.7 | 161761.66 | 169849.74
| Subtotal (Office and Utilities) | 345737.6 | 363024.48 | 381173.7 | 400232.66 | 420243.74
Digital Infrastructure
| Domain Name and Hosting (Per Year) | 100000 | 105000 | 110250 | 115762.5 | 121550.63
| Email Hosting (Per Year) | 50000 | 52500 | 55125 | 57881.25 | 60775.31
| Cloud Services (Per Year) | 50000 | 52500 | 55125 | 57881.25 | 60775.31
| Servers | 150000 | 157500 | 165375 | 173644.25 | 182326.46
| Cloud Storage | 21450 | 22522.5 | 23648.63 | 24831.06 | 26072.61
| Subtotal (Digital Infrastructure) | 371450 | 390022 | 409903.88 | 431090.06 | 453393.32
Maintenance and Security
| For Maintenance | 35750 | 37537.5 | 39414.38 | 41385.09 | 43454.34
| Domain & Hosting Costs | 6435 | 6756.75 | 7094.59 | 7449.32 | 7822.79
| Profile Management Cost | 50050 | 52552.5 | 55180.12 | 57939.13 | 60836.08
| Data Privacy | 50050 | 52552.5 | 55180.12 | 57939.13 | 60836.08
| Updates | 35750 | 37537.5 | 39414.38 | 41385.09 | 43454.34
| SEO Package (Initial & Maintenance) | 112155 | 117762.75 | 123650.88 | 129833.43 | 136325.12
| Testing and Debugging | 100000 | 105000 | 110250 | 115762.5 | 121550.63
| User Experience Testing | 71500 | 75075 | 78828.75 | 82769.19 | 86907.65
| Subtotal (Maintenance and Security) | 461690 | 484952 | 509020.83 | 533610.37 | 559776.32
Marketing and Promotion
| Marketing Campaigns | 500000 | 525000 | 551250 | 578812.5 | 607752.13
| Collaborations | 300000 | 315000 | 330750 | 347287.5 | 364626.88
| Content Creation for Ads | 400000 | 420000 | 441000 | 462050 | 485152.5
| Ads Platform Fees | 150000 | 157500 | 165375 | 173644.25 | 182326.46
| PPC (Pay Per Click) | 20000 | 21000 | 22050 | 23152.5 | 24310.12
| Subtotal (Marketing and Promotion) | 1370000 | 1439500 | 1430625 | 1486946.75 | 1654807.1
Personnel Costs
| Web Developers | 1400000 | 1400000 | 1400000 | 1400000 | 1400000
| UI/UX Designer | 600000 | 600000 | 600000 | 600000 | 600000
| Marketing Specialist | 600000 | 600000 | 600000 | 600000 | 600000
| Customer Support/Community Manager | 400000 | 400000 | 400000 | 400000 | 400000
| Finance/Administrative Officer | 500000 | 500000 | 500000 | 500000 | 500000
| Product Manager | 500000 | 500000 | 500000 | 500000 | 500000
| Data Analyst | 600000 | 600000 | 600000 | 600000 | 600000
| Subtotal (Personnel Costs) | 4600000 | 4600000 | 4600000 | 4600000 | 4600000
Travel and Food
| Food & Travel | 120000 | 126000 | 132300 | 138915 | 145860.75
| Accommodations | 75000 | 78750 | 82687.5 | 86821.88 | 91162.97
| Miscellaneous | 50000 | 52500 | 55125 | 57881.25 | 60775.31
| Subtotal (Travel and Food) | 245000 | 257250 | 270112.5 | 283618.13 | 297798.03
| Grand Total Operational Costs | 7450227.6 | 7714026.83 | 7927035.75 | 8194897.75 | 8493181.54
Financial expenses | Total maintainance and Depciation cost(Rs) | 389,000 | 389,000 | 389,000 | 389,000 | 389,000 | 389,000
| Total Taxes | ₹42,818 | ₹630,561 | ₹1,720,077 | ₹3,373,505 | ₹5,872,069 | ₹9,659,947
| Interest on Term Loan | 13.5% | 13.5% | 13.5% | 13.5% | 13.5% | 13.5%
| Principal Repayment | 0 | 523738.96 | 598986.86 | 685045.97 | 783469.56 | 896034.11
| Particular | year-1 | year-2 | year-3 | year-4 | year-5 | year-6
Particulars | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Income | Users | 30000 | 45000 | 67500 | 101250 | 151875 | 227813
| Website Impressions | 26745000 | 40117500 | 60126250 | 90178125 | 135267656 | 203308968
| App Impressions | 26745000 | 40117500 | 60126250 | 90178125 | 135267656 | 203308968
| Website Revenue (₹) | 2674500 | 4011750 | 6012625 | 9017813 | 13526767 | 20330897
| App Revenue (₹) | 4011750 | 6017625 | 9018938 | 13526719 | 20290148 | 30496345
| Total Ad Revenue (₹) | 6686250 | 10029375 | 15031563 | 22544532 | 33816915 | 50827242
| Operational Costs (₹) | 4470137 | 4604241 | 4743368 | 4885679 | 5031250 | 5182187
| Financial Expenses (₹) | 987215 | 1510954 | 1515732 | 1521379 | 1526699 | 1533544
| Total Costs (₹) | 5457352 | 6115195 | 6259100 | 6407058 | 6557949 | 6715731
| Profit (₹) | 1228898 | 3914180 | 8772463 | 16137474 | 27258965 | 44111511

## Master doc
Cost Item | Cost (INR)
Fixed Costs
Rented Office | 206000
Furniture (Tables, Desks, Chairs, Fan, Water Dispenser) | 150000
Electricity Bills | 139737.6
Installation | 20000
Miscellaneous | 30000
Domain Name and Hosting (Per Year) | 100000
Email Hosting (Per Year) | 50000
Cloud Services (Per Year) | 50000
Total Fixed Cost | 545737.6
Variable Costs
Backend Development for Mobile App | 500000
Content Management System (CMS) | 350000
Integration with Wearables (Photo/Video Capture) | 300000
Website Customization | 300000
Community Interaction Platform | 250000
Security and SSL Setup | 200000
App Design and User Interface (UI) | 200000
Emergency Contacting and Alerts System | 200000
Content Creation and Management | 150000
Servers | 150000
Fake Call and Anonymous Incident Reporting | 150000
Testing and Debugging | 100000
Place Rating System | 100000
SEO Package | 100000
Total Variable Cost | 3250000
Maintenance Costs
Domain & Hosting Costs | 6435
For Maintenance | 35750
Profile Management Cost | 50050
GPS Integration | 20600
Updates | 35750
SEO Package | 12155
Email Hosting (per year) | 7150
Cloud Storage | 21450
Data Privacy | 50050
Data Analytics Tools | 28600
User Experience Testing | 71500
Total Maintenance Cost | 339490
Marketing Costs
Marketing Campaigns | 500000
Collaborations | 300000 | Category | Particular | Qty(nos) | Cost(Rs/Unit) | Total cost(Rs)
Content Creation for Ads | 400000 | Infrastrucuture & Setup | Rented office | 1 | 206000 | 206000
Ads Platform Fees | 150000 |  | Furniture (tables with desks, chairs,fan. water dispenser | 1 | 1,50,000 | 150000
PPC (Pay Per Click) | 20000 |  | Electricity bills | 1 | 1,39,737.6 | 139737.6
Total Marketing Cost | 1370000 |  | Installation | 5 | 800 | 20000
Travel and Food Costs |  |  | Miscellaneous |  | 30000 | 30000
Food & Travel | 120000 |  | Total cost |  |  | 545737.6
Accommodations | 75000 | Infrastructure & Services | Backend Development for mobile app | 1 | ₹500,000 | 500000
Miscellaneous | 50000 |  | Content Management System (CMS) | 1 | ₹350,000 | 350000
Total Travel and Food Cost | 245000 |  | Integration with Wearables (Photo/Video Capture) | 1 | ₹300,000 | 300000
Personnel Costs |  |  | Website Customization | 1 | ₹300,000 | 300000
Web Developers | 1400000 |  | Community Interaction Platform | 1 | ₹250,000 | 250000
UI/UX Designer | 600000 |  | Security and SSL Setup | 1 | ₹200,000 | 200000
Marketing Specialist | 600000 |  | App Design and User Interface (UI) | 1 | ₹200,000 | 200000
Customer Support/Community Manager | 400000 |  | Emergency Contacting and Alerts System | 1 | ₹200,000 | 200000
Finance/Administrative Officer | 500000 |  | Content Creation and Management | 1 | ₹150,000 | 150000
Product Manager | 500000 |  | Servers | 1 | ₹150,000 | 150000
Data Analyst | 600000 |  | Fake Call and Anonymous Incident Reporting | 1 | ₹150,000 | 150000
Total Personnel Cost | 4600000 |  | Testing and Debugging | 1 | ₹100,000 | 100000
Depreciation & Maintenance | 389000 |  | Place Rating System | 1 | ₹100,000 | 100000
Grand Total | 11870227.6 |  | SEO Package | 1 | ₹100,000 | 100000
|  |  | Domain Name and Hosting (Per Year) | - | ₹100,000 | 100000
|  |  | Email Hosting (Per Year) | - | ₹50,000 | 50000
|  |  | Cloud Services (Per Year) | - | ₹50,000 | 50000
|  |  | Total cost |  |  | 3250000
|  | Application & website related | Domain & Hosting costs |  | 6435 | 6435
|  |  | For maintenance | 1 | 35750 | 35750
|  |  | Profile management cost |  | 50050 | 50050
|  |  | GPS integration |  | 20600 | 20600
|  |  | Updates |  | 35750 | 35750
|  |  | SEO Package |  | 12155 | 12155
|  |  | Email Hosting per year |  | 7150 | 7150
|  |  | Cloud storage |  | 21450 | 21450
|  |  | Data privacy |  | 50050 | 50050
|  |  | Data anlytics tools |  | 28600 | 28600
|  |  | User experience testing |  | 100000 | 100000
367990
|  | Marketing & Promotion | 7 |  | 500000 | 500000
|  |  | Collaborations |  | 300000 | 300000
|  |  | Content creation for Ads |  | 400000 | 400000
|  |  | Ads Platform fees |  | 1,50,000 | 150000
|  |  | PPC(Pay Per Click) |  | 20000 | 20000
|  |  | Total cost |  |  | 1370000
|  | Logistics Expenses | Food & Travel |  | 1,20,000 | 120000
|  |  | Accommodations |  | 75000 | 75000
|  |  | Miscellaneous |  | 50000 | 50000
|  |  | Total cost |  |  | 245000
|  | Salaries | Web Developers | 2 | 14,00,000 | 1400000
|  |  | UI/UX Designer | 1 | 6,00,000 | 600000
|  |  | Marketing Specialist | 1 | 6,00,000 | 600000
|  |  | Customer Support/Community Manager | 1 | 4,00,000 | 400000
|  |  | Finance/Administrative Officer | 1 | 4,00,000 | 500000
|  |  | Product Manager | 1 | 5,00,000 | 500000
|  |  | Data analyst | 1 | 6,00,000 | 600000
|  |  | Cyber security specialist | 2 | 700000 | 1400000
|  |  | Legal | 1 | 600000 | 500000
|  |  | Total cost |  |  | 6500000
|  | Depreciation & Maintainence | Depreciation & Maintainance |  | 389000 | 389000
|  |  | Total cost |  |  | 389000
|  |  | Net total cost |  |  | 12667727.6
|  | Sr No | Particulars | Details
|  | 1 | Scheme Name | Digital India mission
|  | 2 | Total Project Cost | 12667727.6
|  | 3 | Term Loan Amount @ 35% | 4433704.66
|  |  | Scheme amount@20% | 2533545.52
|  |  | Angel Investors(% equity)@ 15% | 1900159.14
|  |  | Subsidy amount@30% | 3800318.28
|  |  | Interest Rate | 13.5%
|  |  | Loan Tenure (Years) | 6
|  |  | Monthly EMI Payable | 90889
|  |  | Annual Amount Repaid (₹) | 1099666
|  | Category | Particular | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6
|  | Fixed costs | Rented Office | 206000 | 206000 | 206000 | 206000 | 206000 | 206000
|  |  | Furniture (Tables, Desks, Chairs, Fan, Water Dispenser) | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
|  |  | Electricity Bills | 139737.6 | 139737.6 | 139737.6 | 139737.6 | 139737.6 | 139737.6
|  |  | Installation | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
|  |  | Miscellaneous | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
|  |  | Domain Name and Hosting (Per Year) | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
|  |  | Email Hosting (Per Year) | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  | Cloud Services (Per Year) | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  | Total Fixed Cost | 545737.6 | 545737.6 | 545737.6 | 545737.6 | 545737.6 | 545737.6
|  | Operational cost | Office and Utilities
|  |  | Rented Office | 206000 | 216300 | 227115 | 238471 | 250394 | 262914 | 1400189
|  |  | Electricity Bills | 139737.6 | 146724.48 | 154058.7 | 161761.66 | 169849.74 | 178342.22 | 970474.4
|  |  | Subtotal (Office and Utilities) | 345737.6 | 363024.48 | 381173.7 | 400232.66 | 420243.74 | 441256.22 | 2370663.4
Digital Infrastructure
|  |  | Domain Name and Hosting (Per Year) | 100000 | 105000 | 110250 | 115762.5 | 121550.63 | 127628.16 | 660591.29
|  |  | Email Hosting (Per Year) | 50000 | 52500 | 55125 | 57881.25 | 60775.31 | 63814.08 | 335095.64
|  |  | Cloud Services (Per Year) | 50000 | 52500 | 55125 | 57881.25 | 60775.31 | 63814.08 | 335095.64
|  |  | Servers | 150000 | 157500 | 165375 | 173644.25 | 182326.46 | 191442.78 | 1019788.74
|  |  | Cloud Storage | 21450 | 22522.5 | 23648.63 | 24831.06 | 26072.61 | 27376.24 | 145900.83
|  |  | Subtotal (Digital Infrastructure) | 371450 | 390022 | 409903.88 | 431090.06 | 453393.32 | 466801.34 | 2422650.59
Maintenance and Security
|  |  | For Maintenance | 35750 | 37537.5 | 39414.38 | 41385.09 | 43454.34 | 45626.06 | 242775.37
|  |  | Domain & Hosting Costs | 6435 | 6756.75 | 7094.59 | 7449.32 | 7822.79 | 8215.93 | 43922.38
|  |  | Profile Management Cost | 50050 | 52552.5 | 55180.12 | 57939.13 | 60836.08 | 63877.88 | 290486.12
|  |  | Data Privacy | 50050 | 52552.5 | 55180.12 | 57939.13 | 60836.08 | 63877.88 | 290486.12
|  |  | Updates | 35750 | 37537.5 | 39414.38 | 41385.09 | 43454.34 | 45626.06 | 242775.37
|  |  | SEO Package (Initial & Maintenance) | 112155 | 117762.75 | 123650.88 | 129833.43 | 136325.12 | 143141.37 | 722063.55
|  |  | Testing and Debugging | 100000 | 105000 | 110250 | 115762.5 | 121550.63 | 127628.16 | 660591.29
|  |  | User Experience Testing | 71500 | 75075 | 78828.75 | 82769.19 | 86907.65 | 91253.03 | 486502.62
|  |  | Subtotal (Maintenance and Security) | 461690 | 484952 | 509020.83 | 533610.37 | 559776.32 | 586775.89 | 3135825.74
Marketing and Promotion
|  |  | Marketing Campaigns | 500000 | 525000 | 551250 | 578812.5 | 607752.13 | 638139.76 | 2892154.89
|  |  | Collaborations | 300000 | 315000 | 330750 | 347287.5 | 364626.88 | 382858.22 | 2040022.11
|  |  | Content Creation for Ads | 400000 | 420000 | 441000 | 462050 | 485152.5 | 509410.12 | 2317612.62
|  |  | Ads Platform Fees | 150000 | 157500 | 165375 | 173644.25 | 182326.46 | 191442.78 | 1019788.74
|  |  | PPC (Pay Per Click) | 20000 | 21000 | 22050 | 23152.5 | 24310.12 | 25525.63 | 136038.75
|  |  | Subtotal (Marketing and Promotion) | 1370000 | 1439500 | 1430625 | 1486946.75 | 1654807.1 | 1799056.68 | 7028792.55
Personnel Costs
|  |  | Web Developers | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 8400000
|  |  | UI/UX Designer | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 3600000
|  |  | Marketing Specialist | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 3600000
|  |  | Customer Support/Community Manager | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 2400000
|  |  | Finance/Administrative Officer | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 3000000
|  |  | Product Manager | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 3000000
|  |  | Data Analyst | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 3600000
|  |  | Subtotal (Personnel Costs) | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 27600000
Travel and Food
|  |  | Food & Travel | 120000 | 126000 | 132300 | 138915 | 145860.75 | 153153.79 | 815229.54
|  |  | Accommodations | 75000 | 78750 | 82687.5 | 86821.88 | 91162.97 | 95721.57 | 510934.42
|  |  | Miscellaneous | 50000 | 52500 | 55125 | 57881.25 | 60775.31 | 63814.08 | 335095.64
|  |  | Subtotal (Travel and Food) | 245000 | 257250 | 270112.5 | 283618.13 | 297798.03 | 312689.44 | 1675968.6
|  |  | Grand Total Operational Costs | 7450227.6 | 7714026.83 | 7927035.75 | 8194897.75 | 8493181.54 | 8814343.56 | 48578712.51
|  | Financial expenses | Total maintainance and Depciation cost(Rs) | 389,000 | 389,000 | 389,000 | 389,000 | 389,000 | 389,000 | 389,000
|  |  | Total Taxes | ₹42,818 | ₹630,561 | ₹1,720,077 | ₹3,373,505 | ₹5,872,069 | ₹9,659,947 | 11027877.75
|  |  | Interest on Term Loan | 13.5% | 13.5% | 13.5% | 13.5% | 13.5% | 13.5% | 13.5%
|  |  | Principal Repayment | 0 | 523738.96 | 598986.86 | 685045.97 | 783469.56 | 896034.11 | 0
|  | Particulars | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
|  | Users | 30000 | 45000 | 67500 | 101250 | 151875 | 227813
|  | Website Impressions | 26745000 | 40117500 | 60126250 | 90178125 | 135267656 | 203308968
|  | App Impressions | 26745000 | 40117500 | 60126250 | 90178125 | 135267656 | 203308968
|  | Website Revenue (₹) | 2674500 | 4011750 | 6012625 | 9017813 | 13526767 | 20330897
|  | App Revenue (₹) | 4011750 | 6017625 | 9018938 | 13526719 | 20290148 | 30496345
|  | Total Ad Revenue (₹) | 6686250 | 10029375 | 15031563 | 22544532 | 33816915 | 50827242
|  | Operational Costs (₹) | 4470137 | 4604241 | 4743368 | 4885679 | 5031250 | 5182187
|  | Financial Expenses (₹) | 987215 | 1510954 | 1515732 | 1521379 | 1526699 | 1533544
|  | Total Costs (₹) | 5457352 | 6115195 | 6259100 | 6407058 | 6557949 | 6715731
|  | Profit (₹) | 1228898 | 3914180 | 8772463 | 16137474 | 27258965 | 44111511
|  | Particulars | Year 1 (₹) | Year 2 (₹) | Year 3 (₹) | Year 4 (₹) | Year 5 (₹) | Year 6 (₹)
|  | Net Sales | 6686250 | 10029375 | 15031563 | 22544532 | 33816915 | 50827242
|  | Variable Cost (Operational) | 4470137 | 4604241 | 4743368 | 4885679 | 5031250 | 5182187
|  | Contribution (Net Sales - Variable Cost) | 2216113 | 5425134 | 10288195 | 17658853 | 28785665 | 45645055
|  | Travel & Logistics (@5%) | 334312.5 | 501468.75 | 751578.15 | 1127226.6 | 1690845.75 | 2541362.1
|  | Marketing & Promotion (@5%) | 334312.5 | 501468.75 | 751578.15 | 1127226.6 | 1690845.75 | 2541362.1
|  | Interest (Financial Expenses) | 987215 | 1510954 | 1515732 | 1521379 | 1526699 | 1533544
|  | Depreciation | 389000 | 389000 | 389000 | 389000 | 389000 | 389000
|  | Total Fixed Costs (Excl. Salary) | 2044840 | 2902891.5 | 3407888.3 | 4164832.2 | 5297390.5 | 7005268.2
|  | Break-Even Point (BEP%) | 92.31% | 53.47% | 33.13% | 23.6% | 18.4% | 15.37%
|  | Average BEP: | 39.38%. ​
|  | Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
|  | Net Sales | ₹6,686,250 | ₹10,029,375 | ₹15,031,563 | ₹22,544,532 | ₹33,816,915 | ₹50,827,242
|  | Variable Cost | ₹4,470,137 | ₹4,604,241 | ₹4,743,368 | ₹4,885,679 | ₹5,031,250 | ₹5,182,187
|  | Contribution | ₹2,216,113 | ₹5,425,134 | ₹10,288,195 | ₹17,658,853 | ₹28,785,665 | ₹45,645,055
|  | Total Fixed Costs (Excl. Salary) | ₹2,044,840 | ₹2,902,891 | ₹3,407,888 | ₹4,164,832 | ₹5,297,391 | ₹7,005,268
|  | Profit Before Tax | ₹171,273 | ₹2,522,243 | ₹6,880,307 | ₹13,494,021 | ₹23,488,274 | ₹38,639,787
|  | Tax (25%after availing MAT) | ₹42,818 | ₹630,561 | ₹1,720,077 | ₹3,373,505 | ₹5,872,069 | ₹9,659,947
|  | Profit After Tax | ₹128,455 | ₹1,891,682 | ₹5,160,230 | ₹10,120,516 | ₹17,616,205 | ₹28,979,840
|  | Depreciation | ₹389,000 | ₹389,000 | ₹389,000 | ₹389,000 | ₹389,000 | ₹389,000
|  | Interest | ₹987,215 | ₹1,510,954 | ₹1,515,732 | ₹1,521,379 | ₹1,526,699 | ₹1,533,544
|  | Loan Repayment | ₹1,099,666 | ₹1,099,666 | ₹1,099,666 | ₹1,099,666 | ₹1,099,666 | ₹1,099,666
|  | Total | ₹2,475,881 | ₹2,999,620 | ₹2,964,398 | ₹2,911,045 | ₹3,014,365 | ₹3,011,210
|  | DSCR | 1.09 | 1.27 | 1.74 | 2.1 | 2.21 | 2.32
Average DSCR=1.79
|  | Year | Net Sales (₹) | Variable Costs (₹) | Profit Before Tax (₹) | Tax (₹) | Profit After Tax (₹) | Cash Flows (₹) | Present Value (₹) | Cumulative Cash Flows (₹)
|  | 1 | 6686250 | 4470137 | 2216113 | 554028 | 1662085 | -295368 | -261713 | -295368
|  | 2 | 10029375 | 4604241 | 5425134 | 1356283 | 4068851 | 2708587 | 2396042 | 2413219
|  | 3 | 15031563 | 4743368 | 10288195 | 2572049 | 7716146 | 6108540 | 4646963 | 8521759
|  | 4 | 22544532 | 4885679 | 17658853 | 4414713 | 13244141 | 11124196 | 6059080 | 19645955
|  | 5 | 33816915 | 5031250 | 28785665 | 7196416 | 21589249 | 19188249 | 8073350 | 38834204
|  | 6 | 50827242 | 5182187 | 45645055 | 11411264 | 34233791 | 32491247 | 9139888 | 71325451
|  | IRR | [7 empty] | 27.56%
|  | Particulars | Value
|  | NPV | 6360252.89
|  | IRR | 27.56%
|  | ROI | 15%
|  | B/C Ratio | 1.154
|  | Payback Period | 2.6 years
|  | Profitability Index | 0.94396

## Break Point
Particulars | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Net Sales (Total Ad Revenue) | ₹6,686,250 | ₹10,029,375 | ₹15,031,563 | ₹22,544,532 | ₹33,816,915 | ₹50,827,242
Variable Costs | ₹4,470,137 | ₹4,604,241 | ₹4,743,368 | ₹4,885,679 | ₹5,031,250 | ₹5,182,187
Contribution (Net Sales - Variable Costs) | ₹2,216,113 | ₹5,425,134 | ₹10,288,195 | ₹17,658,853 | ₹28,785,665 | ₹45,645,055
Fixed Costs
Salary | TBD | TBD | TBD | TBD | TBD | TBD
Travel & Logistics (@5%) | ₹223,307 | ₹511,469 | ₹751,578 | ₹1,127,217 | ₹1,690,846 | ₹2,541,362
Marketing & Promotion (@5%) | ₹334,312 | ₹501,469 | ₹751,578 | ₹1,127,217 | ₹1,690,846 | ₹2,541,362
Interest | ₹987,215 | ₹1,510,954 | ₹1,515,732 | ₹1,521,379 | ₹1,526,699 | ₹1,533,544
Depreciation (7% of Total Costs) | ₹381,008 | ₹427,063 | ₹438,137 | ₹448,494 | ₹459,045 | ₹471,102
Total Fixed Costs (excluding Salary) | ₹1,925,842 | ₹2,450,955 | ₹2,856,025 | ₹3,526,313 | ₹4,353,436 | ₹5,489,248
Break-Even Point (BEP%) | 87% | 45% | 28% | 20% | 15% | 12%
Particulars | Year 1 (₹) | Year 2 (₹) | Year 3 (₹) | Year 4 (₹) | Year 5 (₹) | Year 6 (₹)
Net Sales | 6686250 | 10029375 | 15031563 | 22544532 | 33816915 | 50827242
Variable Cost | 4470137 | 4604241 | 4743368 | 4885679 | 5031250 | 5182187
Contribution (Net Sales - Variable Cost) | 2216113 | 5425134 | 10288195 | 17658853 | 28785665 | 45645055
Fixed Costs:
• Travel & Logistics (5%) | 334312.5 | 501468.75 | 751578.15 | 1127226.6 | 1690845.75 | 2541362.1
• Marketing & Promotion (5%) | 334312.5 | 501468.75 | 751578.15 | 1127226.6 | 1690845.75 | 2541362.1
• Depreciation | 389000 | 389000 | 389000 | 389000 | 389000 | 389000
Total Fixed Costs (Excluding Salary) | 1057625 | 1391938 | 1892156 | 2643453 | 3770692 | 5471724
Break-Even Point (BEP%) | 47.75% | 25.69% | 18.38% | 14.98% | 13.12% | 11.98%

## Logical Framework Analysis
Components | Objectives | Indicators | Means of Verification | Assumptions
Goal | Achieve an ROI of over 15% within 6 years. | ROI percentage | Financial statements | Stable user demand
Purpose | Enhance women's safety through the app. | Number of active users | User engagement metrics | Increased awareness of safety issues
Activities | Develop the app, launch marketing campaigns, engage with users, and establish partnerships with local services. | Number of downloads and active users | App store statistics, user feedback | Access to skilled developers
Inputs | Funding, technology, human resources, and partnerships. | Total investment amount | Financial reports, partnership agreements | Sufficient funding secured
Outputs | High-quality safety app with effective features. | User satisfaction ratings, number of safety alerts sent | User reviews, app analytics | Users are willing to pay for premium features

## Project Activities, Tasks, and
Phase | Activity | Sub-Activity
1. Planning | Conduct Market Research | Identify target audience
Analyze competitors
Conduct surveys and focus groups
| Develop Business Plan | Outline project goals
Create financial projections
Establish a timeline for project milestones
Identify potential partners and stakeholders
2. Development | App Design | Create wireframes
Develop user interface (UI) designs
Design user experience (UX) flow
| App Development | Code core functionalities
Implement security features
Integrate third-party services (e.g., payment gateways, GPS)
3. Testing | Quality Assurance | Conduct functional testing
Perform usability testing
Collect feedback from beta testers
| Security Testing | Conduct penetration testing
Implement security audits
Fix identified vulnerabilities
4. Launch | Marketing Campaign | Create promotional materials
Launch social media campaigns
Develop partnerships with local organizations
Organize launch events
| App Launch | Release app on app stores
Monitor app performance post-launch
5. Evaluation | Collect User Feedback | Distribute surveys
Monitor app analytics
Engage with users on social media
| Analyze Performance | Review user engagement metrics
Identify areas for improvement
Prepare a post-launch evaluation report

## Break even point
Net Sales | 6686250 | 10029375 | 15031563 | 22544532 | 33816915 | 50827242
Variable Cost (Operational) | 4470137 | 4604241 | 4743368 | 4885679 | 5031250 | 5182187
Contribution (Net Sales - Variable Cost) | 2216113 | 5425134 | 10288195 | 17658853 | 28785665 | 45645055
Travel & Logistics (@5%) | 334312.5 | 501468.75 | 751578.15 | 1127226.6 | 1690845.75 | 2541362.1
Marketing & Promotion (@5%) | 334312.5 | 501468.75 | 751578.15 | 1127226.6 | 1690845.75 | 2541362.1
Interest (Financial Expenses) | 987215 | 1510954 | 1515732 | 1521379 | 1526699 | 1533544
Depreciation | 389000 | 389000 | 389000 | 389000 | 389000 | 389000
Total Fixed Costs (Excl. Salary) | 2044840 | 2902891.5 | 3407888.3 | 4164832.2 | 5297390.5 | 7005268.2
Break-Even Point (BEP%) | 92.31% | 53.47% | 33.13% | 23.6% | 18.4% | 15.37%
Average BEP: | 39.38%. ​

## DSCR
Debt To Service Ratio
| Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
| Net Sales | ₹6,686,250 | ₹10,029,375 | ₹15,031,563 | ₹22,544,532 | ₹33,816,915 | ₹50,827,242
| Variable Cost | ₹4,470,137 | ₹4,604,241 | ₹4,743,368 | ₹4,885,679 | ₹5,031,250 | ₹5,182,187
| Contribution | ₹2,216,113 | ₹5,425,134 | ₹10,288,195 | ₹17,658,853 | ₹28,785,665 | ₹45,645,055
| Total Fixed Costs (Excl. Salary) | ₹2,044,840 | ₹2,902,891 | ₹3,407,888 | ₹4,164,832 | ₹5,297,391 | ₹7,005,268
| Profit Before Tax | ₹171,273 | ₹2,522,243 | ₹6,880,307 | ₹13,494,021 | ₹23,488,274 | ₹38,639,787
| Tax (25%after availing MAT) | ₹42,818 | ₹630,561 | ₹1,720,077 | ₹3,373,505 | ₹5,872,069 | ₹9,659,947
| Profit After Tax | ₹128,455 | ₹1,891,682 | ₹5,160,230 | ₹10,120,516 | ₹17,616,205 | ₹28,979,840
| Depreciation | ₹389,000 | ₹389,000 | ₹389,000 | ₹389,000 | ₹389,000 | ₹389,000
| Interest | ₹987,215 | ₹1,510,954 | ₹1,515,732 | ₹1,521,379 | ₹1,526,699 | ₹1,533,544
| Loan Repayment | ₹1,099,666 | ₹1,099,666 | ₹1,099,666 | ₹1,099,666 | ₹1,099,666 | ₹1,099,666
| Total | ₹2,475,881 | ₹2,999,620 | ₹2,964,398 | ₹2,911,045 | ₹3,014,365 | ₹3,011,210
| DSCR | 1.09 | 1.27 | 1.74 | 2.1 | 2.21 | 2.32
Average DSCR=1.79

## IRR
IRR
Year | Net Sales (₹) | Variable Costs (₹) | Profit Before Tax (₹) | Tax (₹) | Profit After Tax (₹) | Cash Flows (₹) | Present Value (₹) | Cumulative Cash Flows (₹)
1 | 6686250 | 4470137 | 2216113 | 554028 | 1662085 | -295368 | -261713 | -295368
2 | ######## | 4604241 | 5425134 | 1356283 | 4068851 | 2708587 | 2396042 | 2413219
3 | ######## | 4743368 | ######## | 2572049 | 7716146 | 6108540 | 4646963 | 8521759
4 | 22544532 | 4885679 | 17658853 | 4414713 | 13244141 | ######## | 6059080 | 19645955
5 | 33816915 | 5031250 | 28785665 | 7196416 | 21589249 | 19188249 | 8073350 | 38834204
6 | ######## | 5182187 | 45645055 | 11411264 | 34233791 | 32491247 | 9139888 | ########
IRR | [7 empty] | 27.56%

## Risk Assessment
Risk Factor | Initial Likelihood | Initial Impact | Mitigation Strategies | Likelihood After Mitigation | Impact After Mitigation
User Adoption Resistance | High | Medium | Conduct surveys to understand user concerns; provide testimonials and case studies to build trust. | Medium | Low
Technical Issues | Medium | Medium | Implement rigorous testing and quality assurance before launch; establish a rapid response team. | Low | Low
Data Privacy Concerns | High | High | Develop a clear privacy policy; conduct user education on data safety; ensure compliance with laws. | Medium | Medium
Competitive Landscape | Medium | Medium | Focus on unique features and benefits; conduct market research to identify gaps. | Medium | Medium
Funding and Financial Stability | High | High | Explore multiple funding sources; create a detailed financial plan and budget. | Medium | Medium
Marketing Effectiveness | Medium | Medium | Develop targeted marketing campaigns; utilize social media and influencers for outreach. | Medium | Medium
User Engagement | High | Medium | Introduce gamification and incentives for regular use; gather user feedback for continuous improvement. | Medium | Low
Legal and Regulatory Compliance | Medium | High | Consult legal experts; ensure transparency in data usage and storage; stay updated on regulations. | Low | Low
Technological Advancements | Medium | Medium | Regularly update the app; invest in research to stay ahead of technological trends. | Medium | Medium
Social and Cultural Factors | Low | Medium | Conduct awareness campaigns and community engagement activities to promote safety app usage. | Low | Low
Economic Factors | Medium | Medium | Offer flexible pricing and subscription models; monitor economic trends and adjust strategies. | Medium | Medium
Market Trends | Medium | Medium | Stay informed about market shifts; conduct regular user surveys to understand changing needs. | Medium | Medium

## Fishbone diagram2
Fish bone diagram
Resource Accessibility
Regulatory Compliance
Skill Development
Decision-Making Processes
Economic Empowerment
Information Shielding
| Operational Transparency | Social Empowerment
Social & political Issues
Advocacy
Governance
Empowerment
Integrity

## Issue Tree Diagram 2
Advocacy
| Resource Accessibility |  |  | Skill Development
Lack of awareness of resources |  | Limited internet or data access | Lack of training opportunities |  | Limited access to educational content
Onboarding tutorial, resources tab |  | Offline mode, zero-data plans | Partner with training organizations |  | Provide in-app learning resources
Integrity
| Information Shielding |  |  | Operational Transparency
Risk of data being hacked |  | Inconsistent data handling practices | Lack of transparent operations |  | Unclear user privacy policies
Implement strong data encryption measures |  | Set clear data management protocols | Regular audits, publish transparency reports |  | Simplify and communicate privacy policies
Governance
| Regulatory Compliance |  |  | Decision-Making Processes
Non-adherence to legal regulations |  | Lack of staff training | Lack of transparency in decisions |  | Insufficient stakeholder involvement
Establish clear compliance protocols |  | Conduct regular compliance training sessions | Implement clear decision-making guidelines |  | Encourage stakeholder feedback mechanisms
Empowerment
| Economic Empowerment |  |  | Social Empowerment
Wage disparity |  | Limited job opportunities | Limited access to support networks |  | Social stigma or discrimination
Advocacy for equal pay and policies |  | Skill development programs | Connect with local NGOs |  | Awareness campaigns, community engagement

## Fishbone diagram
Fishbone Diagram
Lack of local infrastructure
Data Security
| Compliance with legal regulations |  | Complex regulatory landscapes
Trust & Credibility
|  | Dependability of Service Providers |  | Talent acqusition challenges
| Quality of External services for testing & debugging |  | Need for cyber security professionals
Technical and legal Issues
Surroundings
Skills
Systems
Suppliers

## ISsue trees1
Issue Trees for Fishbone diagram 1
System related issues
| Data Security | [7 empty] | Trust & Credibility |  |  | Compliance with legal regulations
Gaps in security/Data breaches |  |  |  | Insufficient Data Anonymization |  |  | Need for enhanced API security | User data privacy considerations |  | Limited User Testimonials and Success Stories | Non-Compliance with location based Data Protection Laws |  | Cross-Border Data Transfer Issues
Strong encryption with multifactor authentication |  |  |  | Using tokenization to replace sensitive data with unique identifiers. |  |  | Secure APIs with authentication tokens | Adopting transparent data-handling policies & Provide easy access to privacy settings |  | Using positive narratives in marketing campaigns & highlighting successful outcomes | Regularly review and update the app’s privacy policies |  | Storing data in regions compliant with the local data protection laws
Surroundings related issues
|  |  | Conduct thorough market research | [5 empty] | Complex regulatory landscapes |  |  | Community resistance
Inadequate Internet Connectivity & Poor network coverage |  |  |  | Limited Access to Power Supply |  |  | Insufficient Infrastructure for Device Usage | Lack of clarity in regulations |  | Frequent Changes in Regulations | Limited awareness of app & website's benefits |  | Mismatched App Features with Community Needs
Partnering with local internet service providers & making offline features available |  |  |  | Partnering with NGOs or local organizations to provide energy efficient solutions |  |  | Ensuring that app is light-weight and compatible with older devices | Engaging Legal Experts & making a compliance list |  | Hiring compliance experts | Implementing educational outreach initiatives & creating easy to understand marketing strategies |  | Conducting thorough market research & customizing app features based on feedbacks
Skill related issues
| Talent acqusition challenges | [7 empty] | Insufficient Knowledge of Regulations |  |  | Skill development gaps
Limited Access to Talent Pool |  |  |  | Limited Awareness of the Brand |  |  |  | Lack of Formal Training |  | Rapidly Changing Regulations | Outdated Training Programs |  | Insufficient Resources for Training
Enhancing Recruitment Strategies |  |  |  | Engaging in Community Outreach |  |  |  | Implementing ongoing training programs |  | Hiring or consulting with legal experts | Implementing ongoing training programs |  | encouraging participation in relevant courses and certification
Supplier related issues
|  | Quality of exernal services for testing & debugging | [6 empty] | Dependability of Service Providers
| Inadequate Communication with Service Providers |  |  |  | Inconsistent Testing Standards |  |  | Inconsistent Uptime |  | Hidden supplier costs
| Scheduling regular check-ins and collaborative sessions with service providers |  |  |  | Developing and sharing a standardized testing framework |  |  | Regularly evaluating supplier performance |  | Negotiating clear contracts with vendors

## Stakeholder matrix
Stakeholder Matrix
| KEEP THEM SATISFIED (High power low interest) Technology providers, NGO and Socail organizations |  | MANAGE THEM CLOSELY (High powerh High interest) Investors , Women users, Law enforcement agencies
Power
| MONITOR (Low power low interest) Competitors |  | KEEP INFORMED (Low Power low interest) Employees
Interest

## Stakeholders Profiles and Score
Stakeholders Profiles and Scores
Stakeholder | Power | Interest | Influence | Impact | Expectations | Proximity
Investors | 8 | 7 | 8 | 9 | 9 | 5
Women Users | 4 | 10 | 6 | 8 | 8 | 9
Employees | 5 | 8 | 7 | 7 | 7 | 8
NGOs & Social Organizations | 6 | 8 | 6 | 7 | 8 | 6
Competitors | 5 | 5 | 7 | 4 | 5 | 4
Local Law Enforcement | 9 | 6 | 9 | 9 | 8 | 6
Influencers | 5 | 7 | 8 | 6 | 7 | 5
Technology Partners | 7 | 7 | 6 | 8 | 7 | 5

## STakeholder scores
Stakeholders Profiles and Scores
Stakeholders Profiles and Scores
Stakeholder | Power | Interest | Influence | Impact | Expectations | Proximity
Investors | 8 | 7 | 8 | 9 | 9 | 5
Women Users | 4 | 10 | 6 | 8 | 8 | 9
Employees | 5 | 8 | 7 | 7 | 7 | 8
NGOs and Social Organizations | 6 | 8 | 6 | 7 | 8 | 6
Competitors | 5 | 5 | 7 | 4 | 5 | 4
Local Law Enforcement | 9 | 6 | 9 | 9 | 8 | 6
Influencers | 5 | 7 | 8 | 6 | 7 | 5
Technology Partners | 7 | 7 | 6 | 8 | 7 | 5